## Sheet1
ITF python requirement
date | description | priority | submitter | comments | status
2017-07-06 | FPGA rework has some empty lines, can remove them? | 2 | libo | Not must, nice to have | Done
2017-07-06 | when select old weeks, the file name will still be the latest week's info (2017WWxy_Silver/Gold/BKC) | 2 | libo | Not must, nice to have | Done
2017-07-06 | detect available memory and see if it is enable for ITF, and prompt to user the requirements. This function can be enabled/disabled by user. | 3 | libo | Not must, nice to have | Done
2017-07-06 | force to close the generated excel file after sent email, in case user didn't close it. This function can be enabled/disabled by user. | 3 | libo | Not must, nice to have | Done
2017-07-06 | detect if there is any exsiting excel process, and prompt user to save and close it. This function can be enabled/disabled by user. | 3 | libo | Not must, nice to have | Done
2017-07-06 | support auto running ITF on all selected projects in configuration. the configuration is the last configuration. This function can be enabled/disabled by user. | 3 | libo | Not must, nice to have | Done
2017-07-06 | enable communication with HPQC to download test case info and update to excel, upload test plan in HPQC | 1 | libo | Not urgent, Libo will book meeting with OSS team
2017-07-06 | enable gather SW/IFWI configuration from tool before run silver test, not from OSS. Keep update configuration from OSS aftern silver test. | 1 | libo | Not urgent, Libo will book meeting with validation team | Done
2017-07-28 | in Mapping table "Mapping area", highlight if the relevancy value > 0 (current it will highlight only if it = 1) | 1 | libo | urgent
2017-07-28 | Generate html data for email after users review and save excel (current it is before user review and save excel) | 1 | libo | urgent
2017-08-09 | Format "Saved Test Case (%)", "Saved Efforts (%)", "Missed Sighting (%)" in Trend table. Format is like: 50%. No decimal. Please use the latest Excel template. | 1 | libo
2017-08-09 | Add "Saved Test Case (%)", "Saved Efforts (%)", "Missed Sighting (%)" in Trend chart. For example: if it is 50%, then the value is 50. | 1 | libo
2017-08-09 | In Trend chart, change Strings: x-axis: Value -> Value, y-axis: Weeks -> Week, Purley-FPGA Excel Table Charts (Line Charts) -> Purley-FPGA BKC Trend. | 1 | libo